## Sheet1
Sl. No | DATE | TIME | Acitivity Title | Activity Description | #Error | Error Detail | Error Fixed | Activity Status | Deadline
1 | 2020-11-11 | 17:45 | Project Senario | Created project structure,activity tracker file and empty documentation file | Nil | Nil | Nil | Completed | 2020-11-12
2 | 2020-11-12 | 18:00 | Sql code | Created 5 tables in mysql and model classes | Nil | Nil | Nil | Completed | 2020-11-13
3 | 2020-11-15 | 8:15 | Model package code | Coded all model classes | Nil | Nil | Nil | Completed | 2020-11-16
4 | 2020-11-17 | 6.00 PM | dao package code | Coded all dao classes ,config,entry package | Nil | Nil | Nil | Completed | 2020-11-18
5 | 2020-11-19 | 9:30 | daoImpl package code | coded all daoImpl classes | Nil | Nil | Nil | Completed | 2020-11-20
6 | 2020-11-20 | 10:00 | Remaining classes code | coded all contoller package classes and tested CRUD menu | Nil | Nil | Nil | Completed | 2020-11-21
7 | 2020-11-21 |  | Login | created structure of login frame | Nil | Nil | Nil | Completed | 2020-11-23
8 | 2020-11-23 |  | HRAHome | created structure of HR frame | Nil | Nil | Nil | Completed | 2020-11-25
9 | 2020-11-25 |  | EMPHome | created structure of employee frame | Nil | Nil | Nil | Completed | 2020-11-27
10 | 2020-11-27 |  | PMEHome | created structure of project manager frame | Nil | Nil | Nil | Completed | 2020-11-29
11 | 2020-11-29 |  | Frame test | testing of login frame | Nil | Nil | Nil | Completed | 2020-12-01
12 | 2020-12-01 |  | Implementation of login frame | Implemented functions of Login | Nil | Nil | Nil | Completed | 2020-12-02
13 | 2020-12-02 |  | Implementation of HRA frame | Implemented all functions of HRA home page | Nil | Nil | Nil | Completed | 2020-12-03
14 | 2020-12-03 |  | Implementation of EMP frame | Implemented all functions of EMP home page | Nil | Nil | Nil | Completed | 2020-12-05
15 | 2020-12-05 |  | Implementation of PME frame | Implemented all functions of PME home page | Nil | Nil | Nil | Completed | 2020-12-07
16 | 2020-12-07 |  | view package | completed view package | Nil | Nil | Nil | Completed | 2020-12-10
17 | 2020-12-10 |  | front end and back end | front end and back end process | Nil | Nil | Nil | Completed | 2020-12-12